## Issues Tracker
App / Module | Issue # | Issue Description | Root Cause | Resolution | Status
IDP UI | 1 | Blank page - app would not render at all | Angular 21 zoneless change detection required provideZonelessChangeDetection(); zone.js polyfills were still included causing conflicts | Added provideZonelessChangeDetection() in app.config.ts; removed zone.js from package.json and angular.json polyfills | Resolved
IDP UI | 2 | API calls failing - cycles not loading | cycle-state.service.ts had hardcoded /api/cycles base URL instead of using environment.apiPrefix; requests bypassed proxy and hit wrong backend | Updated cycle-state.service.ts to use environment.apiPrefix so calls route through /idp-app/api proxy to port 8008 | Resolved
IDP UI | 3 | Debug console.log statements cluttering output | Leftover debugging logs in main.ts from troubleshooting the blank page issue | Cleaned up all debug log statements from main.ts | Resolved
Performance Hub API | 1 | API server crash on startup - seed data fails | Column review_level does not exist in kpi_quarter_actuals table; DB schema was outdated after GitHub code sync | Added missing columns (review_level, review_status, review_comments, reviewed_by_id, reviewed_at) via ALTER TABLE | Resolved
Performance Hub API | 2 | Missing sdbip_revision_logs table | New table referenced in updated schema from GitHub but never created in the database | Created sdbip_revision_logs table via SQL DDL with all required columns and foreign keys | Resolved
Performance Hub API | 3 | API server port conflict - Replit artifact assigns port 8080 (used by POS UI) | Replit artifact system auto-assigns PORT=8080 to API server workflow; POS UI already occupies port 8080; API server killed by Replit | Hardcoded port 6800 in api-server/src/index.ts; spawn API server as child process from POS API (same pattern as Budget API) | Resolved
Performance Hub UI | 4 | Perf-app running on random port 18156 instead of expected 5173 | Replit artifact system assigns arbitrary port; vite.config.ts relied on PORT env var which Replit overrode | Hardcoded port=5173 and basePath=/insights-app directly in vite.config.ts | Resolved
Performance Hub UI | 5 | Duplicate perf-app instances (artifact + POS API child process) | Both artifact workflow and POS API tried to start perf-app on port 5173; second instance fell back to 5174 | Removed perf-ui child process spawn from POS API; let artifact workflow handle UI on port 5173 | Resolved
Performance Hub | 6 | Source code out of sync with GitHub repo | Local codebase had older version; missing new pages (review workflows, dashboard sub-pages, SDBIP revision/approval) | Clean-synced all source from Ruaninzaloems/Insight-Performance-Hub master branch on GitHub | Resolved
SCM UI | 1 | Dashboard shows Internal server error | SCM API requires SQL Server (Azure SQL) on port 3002 which is not available in this Replit environment | Cannot fix without SQL Server connection credentials - external dependency | Open
SCM API | 2 | SCM API will not start | SCM API is a .NET app targeting SQL Server (Azure SQL); connection string points to unavailable Azure SQL instance | Requires valid Azure SQL Server credentials; constraint: do NOT modify SCM source code | Open
ASSETS-UI (Shell) | 1 | Insights module label needed renaming to Performance | Module was originally named Insights in sidebar chip and login badge; user requested rename | Updated shell.component.ts (module chip + brand header) and login.component.ts (badge); internal key remains insights | Resolved
ASSETS-UI (Shell) | 2 | Proxy not reaching Performance Hub services | proxy.conf.json /insights-app/ pointed to port 5173 and /insights-app/api to port 6800; services not running on those ports initially | Fixed by ensuring Performance Hub API runs on 6800 and UI on 5173 as proxy expects | Resolved
POS API | 1 | Proxy errors for /insights-app/ in logs | POS API Angular child process proxy tried to forward /insights-app/ to port 5173 before Performance Hub UI was started | Performance Hub UI now starts via artifact workflow on port 5173; POS API spawns only the API server | Resolved
Payroll | 1 | Payroll app not accessible | Payroll UI on port 8099 and API via external ngrok tunnel - ngrok tunnel not active/reachable | External dependency - requires ngrok tunnel to be running for API access | Open

## Summary
App / Module | Total Issues | Resolved | Open
IDP UI | 3 | 3 | 0
Performance Hub API | 3 | 3 | 0
Performance Hub UI | 2 | 2 | 0
Performance Hub | 1 | 1 | 0
SCM UI | 1 | 0 | 1
SCM API | 1 | 0 | 1
ASSETS-UI (Shell) | 2 | 2 | 0
POS API | 1 | 1 | 0
Payroll | 1 | 0 | 1
TOTAL | 15 | 12 | 3