## UnbundleCosting
Thaba Chweu Municipality Mast Lights Project |  |  | Project Code |  |  | ___________________________________________________
Financial System Spend |  |  | 3617976.28 |  |  |  | Financial Spending |  |  | 566801.0096 | 2531711.1761 | 1037623.7149 | 4136135.9005 | -518159.6205
Bill of Quantities |  |  | 3868390.05 |  |  |  | Actual Unit Cost |  |  | 28340.0505 | 126585.5588 | 51881.1857
Ratio |  |  | 1.0692 |  |  |  | Actual Survey |  |  | 20 | 20 | 20
[7 empty] | BoQ |  |  | 20 | 20 | 20
[7 empty] | Unit |  |  | ea | ea | ea
ITEM NO | PAYMENT REFERS | ITEM DESCRIPTION | AMOUNT TENDERED |  |  |  |  | P & G | General | High Mast Light
|  |  | UNIT | QUANTITY | RATE | AMOUNT |  |  |  | Plynth | Mast | Light
Schedule 1
PRELIMINARY & GENERAL
| 1 | Preliminary & General | PC SUM | 0 |  | 301400 |  | 301400 | [5 empty] | 0
|  | Retention |  |  |  | 184209.05 |  | 184209.05 | [5 empty] | 0
|  | Supply, Installation, testing and commissioning of Mast Structures | [11 empty] | 0
| 1 | Supply of 3-rope hoisting Highlight mast with brackets and foundation bolts ex works | EA | 20 | 30373.3479 | 607466.958 |  |  |  |  | 607466.958 |  |  | 0
| 2 | Mast internal glass fibre IP30 Db with photo cell, IP65 Splitterbox and 5core x 2,5mm training cable (No surge protection) | EA | 20 | 3239.8238 | 64796.4755 |  |  | 64796.4755 |  |  |  |  | 0
| 3 | Concrete foundation complete with soil and concrete cube tests | EA | 20 | 15186.6739 | 303733.479 |  |  |  | 303733.479 |  |  |  | 0
| 4 | Earthing: Supply and Install Sectionalpoles standard system consisting of 2x2.1m earth spikes complete with 2 x 70 mm² copper conductor wih 2x brass clamps | EA | 20 | 30373.3479 | 607466.958 |  |  |  |  | 607466.958 |  |  | 0
| 5 | Delivery of masts to site (Per Load) | EA | 4 | 15186.6739 | 60746.6958 |  |  |  |  | 60746.6958 |  |  | 0
| 6 | Assemble and erection of mast (By supplier to ensure mast Guarantee) | EA | 8 | 10124.4493 | 80995.5944 |  |  |  |  | 80995.5944 |  |  | 0
| 7 | Luminaires complete with lamp | EA | 180 | 2925.9658 | 526673.8526 | [5 empty] | 526673.8526 |  | 0
| 8 | Mounting and wiring of luminaires per mast (assuming light fittingd are on site abd aiming angles provided before hand) | EA | 20 | 1468.0451 | 29360.903 | [5 empty] | 29360.903 |  | 0
| 9 | Electrical Connections | sum | 1 | 809955.944 | 809955.944 |  |  | 809955.944 |  |  |  |  | 0
[6 empty] | 0 | [7 empty] | 0
|  | Servicing Equipment (1 set per site is recommended) |  |  |  | 0 | [7 empty] | 0
| 9 | Single drum which complete with stainless steel rope and winch | EA | 1 | 32398.2378 | 32398.2378 |  |  | 32398.2378 |  |  |  |  | 0
| 10 | Hydrualic powertool with remote control | EA | 1 | 6074.6696 | 6074.6696 |  |  | 6074.6696 |  |  |  |  | 0
| 11 | Test lead - in order to test operation of lights if mast is lowered | EA | 1 | 101244.493 | 101244.493 |  |  | 101244.493 |  |  |  |  | 0
| 12 | Negotiations and application to supply authorities | sum | 1 | 151866.7395 | 151866.7395 |  |  | 151866.7395 |  |  |  |  | 0
[6 empty] | 3868390.05 |  | 485609.05 | 1166336.5593 | 303733.479 | 1356676.2062 | 556034.7555 | 3868390.05 | 0
[7 empty] | Distribute General Values |  | -1166336.5593 | 159830.517 | 713909.6426 | 292596.3998 | 0
[8 empty] | 485609.05 | 0 | 463563.996 | 2070585.8487 | 848631.1553 | 3868390.05
[7 empty] | Distribute P & G | -485609.05 |  | 66546.0967 | 297239.2321 | 121823.7211 | 0
[8 empty] | 0 | 0 | 530110.0927 | 2367825.0809 | 970454.8764 | 3868390.05
[7 empty] | Unit Cost on BoQ |  |  | 26505.5046 | 118391.254 | 48522.7438

## Finance_Invoices
Period | Votenumber | Vote Description | Transaction Type | Reference | TranDate | Debit Amt | Credit Amt | Transaction Description | Originating Description | Bnk | Cheque | Cheque Amt | Status | Payee
201711 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Sundry Payments |  | 20141107 | 1188522 | 0 | RJJ PROJECT MANAGEMENT (PTY)LTD | Cheque No : 16459 Bank No : 777 | 777 | 16459 | 1354915.08 | Cashed | RJJ PROJECT MANAGEMENT (PTY)LTD
201711 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Sundry Payments |  | 20141203 | 118554.69 | 0 | INGPLAN CONSULTING ENGINEERS (PTY)LTD | Cheque No : 16682 Bank No : 777 | 777 | 16682 | 135152.35 | Cashed | INGPLAN CONSULTING ENGINEERS (PTY)LTD
201711 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Sundry Payments |  | 20141203 | 809456.95 | 0 | RJJ PROJECT MANAGEMENT (PTY)LTD | Cheque No : 16685 Bank No : 777 | 777 | 16685 | 922780.92 | Cashed | RJJ PROJECT MANAGEMENT (PTY)LTD
201802 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Sundry Payments |  | 20150225 | 902983 | 0 | RJJ PROJECT MANAGEMENT (PTY)LTD | Cheque No : 17367 Bank No : 777 | 777 | 17367 | 1029400.62 | Cashed | RJJ PROJECT MANAGEMENT (PTY)LTD
201802 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Ledger Journals | 153 | 20150513 | 74068.21 | 0 | CORRECTION OF EXPENDITURE TO CORRECTED VOTES | CORRECTION OF EXPENDITURE TO CORRECTED VOTES
201802 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Ledger Journals | 153 | 20150513 | 365255 | 0 | CORRECTION OF EXPENDITURE TO CORRECTED VOTES | CORRECTION OF EXPENDITURE TO CORRECTED VOTES
201802 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Ledger Journals | 153 | 20150513 | 70220.4 | 0 | CORRECTION OF EXPENDITURE TO CORRECTED VOTES | CORRECTION OF EXPENDITURE TO CORRECTED VOTES
201802 |  | PLANT AND EQUIPMENT(HIGH MAST LIGHT ) | Ledger Journals | 153 | 20150513 | 88916.03 | 0 | CORRECTION OF EXPENDITURE TO CORRECTED VOTES | CORRECTION OF EXPENDITURE TO CORRECTED VOTES
[6 empty] | 3617976.28 | [5 empty] | 3442248.97

## Values FAR
ComponentId | Asset | Component | EUL | Financial_Status | Description | Project_Name | length_qty | width | area | AQC
793230441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793309441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793469441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793506441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793810462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793843462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793847441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793924462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
793959462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
794006462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
794736441 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803095460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803135460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803213460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803249460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803314460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803348460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803416460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803460460 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
803553462 | High Mast | High Mast |  | ADD | 30 m Steel High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 126585.5588
[7 empty] | 20 |  |  | 2531711.1761 | 0
793252441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793316441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793478441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793524441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793817462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793859462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793867441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793942462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
793975462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
794022462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
794754441 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803114460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803151460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803229460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803265460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803328460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803364460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803432460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803476460 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
803559462 | High Mast | High Mast Light |  | ADD | 9 Lights | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 51881.1857
[7 empty] | 20 |  |  | 1037623.7149 | 0
793243441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793333441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793491441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793515441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793830462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793850462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793858441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793933462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
793966462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
794013462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
794745441 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803106460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803143460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803221460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803257460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803320460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803356460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803424460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803468460 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
803571462 | High Mast | Plynth |  | ADD | Concrete Plynth for High Mast | Lekwa Teemane High Mast Lights Phase 2 | 1 |  |  | 28340.0505
[7 empty] | 20 |  |  | 566801.0096 | 0